## Sheet1
When: 2021/10/05 03:00 PM |  | Who: Group21 | Application: Timups
ID | Scenario Title | Status | Scenario | Remarks
1 | Home page(index.html) | Pass | Given index.html lauched, When the user clicks the interface switch button, Then it shows the same thing. | You can add more photos and description
2 | Home page(index.html) | Fail | Given index.html lauched, When the user clicks commodity navigation interface, Then it's not showing anything. | You can add a proper link to this interface
3 | Home pages(index.html) | Pass | Given index.html lauched, When the user clicks Upper navigation button, Then it's switching between different interfaces according to the plan. | You can add more photos and description
4 | Home page(index.html) | Fail | Given index.html lauched,When the user clicks "watches", Then it's entering a new page but "watches" chaning to "products". | You can change the name in the first page
5 | Home page(index.html) | Fail | Given index.html lauched, When the user clicks Specific function introduction, Then it's not showing anything. | You can add a proper link to interface
6 | Products page(products.html) | Fail | Given products.html lauched, When the user clicks "view all", Then it's not showing anything. | You can add a proper link to this button
7 | About page(about.html) | Fail | Given about.html lauched, When the user clicks "read more", then it's not showing anything. | You can add a proper link to this button
8 | About page(about.html) | Fail | Given about.html lauched, When the user clicks facebook, twitter, linkin, instagram logo, Then it's not showing anything. | You can add a proper link to these logo
9 | About page(about.html) | Fail | Given about.html lauched, When the user clicks "local", Then it's not showing anything. | You can add a proper link to "local"
10 | About page(about.html) | Fail | Given about.html lauched, When the user clicks "subscribe", Then it's not showing anything. | You can add a proper link to this button
11 | Contact page(contact.html) | Fail | Given contact.html lauched, When the user clicks "send", Then it's not showing anything. | You can add a proper link to this button
12 | Orders page(orders.html) | Fail | Given orders.html lauched, When the user clicks "view order", Then it's not showing anything. | You can add a proper link to this button
13 | Orders page(orders.html) | Fail | Given orders.html lauched, When the user clicks "track shipment", Then it's not showing anything. | You can add a proper link to this button
14 | Orders page(orders.html) | Fail | Given orders.html lauched, When the user clicks "buy it again" and "request a return" , Then it's not showing anything. | You can add a proper link to this button
15 | Orders page(orders.html) | Fail | Given orders.html lauched, When the user clicks the product name under the "shipped", Then it's not showing anything. | You can add a proper link to this option