## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
E-SHOPPING
Group 21 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Dazhong sheng | Keyi wang | Yufan li | Mengze chen
Project Start Date: | 2021-09-14 |  |  |  |  | September | [13 empty] | October | [34 empty] | November
Scrolling Increment: | 5 | time axis 2021-09-19 to 2021-11-13
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-09-19 to 2021-11-13
Iteration 01
Iteration planning and meeting | Milestone | All members | 100% | 2021-09-14 | 1
Complete stakeholder register | High Risk | All members | 100% | 2021-09-15 | 5
Design persona | Low Risk | Dazhong sheng | 100% | 2021-09-20 | 8
Review and test persona | Med Risk | Keyi wang | 100% | 2021-09-24 | 4
Complete progress report | On Track | Dazhong sheng | 100% | 2021-09-28 | 3
Milestone | Milestone |  | 100% | 2021-10-01 | 1 | bar: 2021-10-01
Iteration 02
Iteration planning and meeting | Milestone | All members | 100% | 2021-10-04 | 1 | bar: 2021-10-04
Complete Resource Requirement List | Med Risk | Yufan li | 100% | 2021-10-05 | 10
Make Gantt chart | Low Risk | Keyi wang & Dazhomg sheng | 100% | 2021-10-12 | 8
Complete progress report | On Track | Dazhong sheng | 100% | 2021-10-20 | 3
Milestone | Milestone |  | 100% | 2021-10-23 | 1 | bar: 2021-10-23
Iteration 03
Iteration planning and meeting | Milestone | All members | 100% | 2021-10-26 | 1 | bar: 2021-10-26
Complete risk Register | High Risk | Keyi wang & Yufan li | 100% | 2021-10-27 | 7
Complete user acceptance test results | High Risk | Yufan li | 100% | 2021-11-02 | 7
Complete progress report | On Track | Dazhong sheng | 100% | 2021-11-09 | 3
Milestone | Milestone |  | 100% | 2021-11-12 | 1 | bar: 2021-11-12

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-11 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-12 to 2022-01-06
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-11 | 3 | F: 2; S: 2
Task 2 | Milestone |  |  | 2021-11-16 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2021-11-08 | 10
Task 4 | Milestone |  |  | 2021-12-01 | 1 | bar: W
Task 5 | Med Risk |  | 10% | 2021-11-17 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-17 | 13
Task 2 | On Track |  | 50% | 2021-11-19 | 9
Task 3 | Low Risk |  | 33% | 2021-11-24 | 11
Task 4 | Milestone |  |  | 2021-11-26 | 1 | bar: F
Task 5 |  |  |  | 2021-11-27 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-26 | 4
Task 2 | Med Risk |  |  | 2021-11-29 | 14
Task 3 | On Track |  |  | 2021-12-14 | 6
Task 4 | Goal |  |  | 2021-12-18 | 3 | S: 2; S: 2; M: 2
Task 5 | Low Risk |  |  | 2021-11-17 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-21 | 15
Task 2 |  |  |  | 2022-01-04 | 5
Task 3 | Milestone |  |  | 2022-02-15 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-11 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-16 to 2022-01-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-16 to 2022-01-10
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-11 | 3
Task 2 | Milestone |  |  | 2021-11-16 | 1 | bar: 2021-11-16
Task 3 | Low Risk |  | 50% | 2021-11-08 | 10
Task 4 | Milestone |  |  | 2021-12-01 | 1 | bar: 2021-12-01
Task 5 | Med Risk |  | 10% | 2021-11-17 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-17 | 13
Task 2 | On Track |  | 50% | 2021-11-19 | 9
Task 3 | Low Risk |  | 33% | 2021-11-24 | 11
Task 4 | Milestone |  |  | 2021-11-26 | 1 | bar: 2021-11-26
Task 5 |  |  |  | 2021-11-27 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-26 | 4
Task 2 | Med Risk |  |  | 2021-11-29 | 14
Task 3 | On Track |  |  | 2021-12-14 | 6
Task 4 | Goal |  |  | 2021-12-18 | 3 | 2021-12-18: 2; 2021-12-19: 2; 2021-12-20: 2
Task 5 | Low Risk |  |  | 2021-11-17 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-21 | 15
Task 2 |  |  |  | 2022-01-04 | 5
Task 3 | Milestone |  |  | 2022-02-15 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one